# OneNote-style weekly notes: input for "Weekly Project Summary"

Rough, unstructured notes a project analyst jotted across the week (as they would appear on a OneNote page). In the lab, Copilot drafts a clean weekly project summary from these, grounded only on what is here.

Project: North Delta Levee Rehabilitation, week of 2026-04-06

Mon

- Kickoff with geotech consultant. First boring logs due Thu.

- PC-006 (nesting bird avoidance) at risk. Tree removal must finish before May 1 or it slips a season.

Tue

- Public workshop #2 recap: 78 attendees. Main concern was construction traffic on River Rd.

- Grant reimbursement #3 submitted, 1.1 million dollars.

Wed

- Reach 3 design review. 60% design accepted with two comments (drainage, access ramp slope).

- Right-of-way: landowner #2 signed. One parcel remaining.

Thu

- Boring logs came in a day early. No surprises so far.

- Cost risk on borrow material still open. PM wants a number by next Wed.

Fri

- Reconciled milestone dates with the three regional teams. Aligned on a single tracker.

- PC-013 (quarterly mitigation monitoring) flagged at risk, monitor availability.

- Reminder: monthly leadership report due the 5th, template ready.

Open items / next week

- Close drainage and ramp-slope comments on Reach 3.

- Get borrow-material cost number to PM by Wed.

- Confirm bird monitor and finish tree removal before May 1.